# M21 - Project Evaluation Summary

Friday 18th July 2008

Main points:

General issues

- Only 5 months to go before we must wind-up

- Unexpected problems - Ann’s illness + Batel’s departure has created difficulties

- These are compounded by financial constraints [College policies, etc]

- Spending more on the internal research team and less on external experts has been a mixed blessing – good for morale, not so good for our credibility

- The project has achieved many successes in terms of knowledge and insights, but has [seemed to?] slow down in terms of outcomes

- There are too many tools to develop and evaluate within the time available

- Publication outcomes are strong, and will be stronger once the website and videos are complete

- Key challenges:

  - Organization – tension between write-up and implementation

  - Finances – achieving both, to budget / quality / timescale

  - Delivery – showing proof of concept at the practical level

Possibilities for workshops

We have learned a great deal (some knowledge less transferrable)

Can we use this knowledge to conduct commercial work?

- E.g. Greengaged (Design Council) 15-19, 22-23 September 2008

- E.g. Casa Décor (with designers from Japan, etc) 13th October 2008

- E.g. Creative Process – offer Andrew a free introduction

- E.g. Futerra – are interested to continue working with us

- E.g. should we return to Arcola with a more specific offer?

- E.g. we could try a commercial (friendly) design/advertising company

Publication plans

- Handbook – how does this objective look?

- 2 other books – implicates Clive Dilnot and Naomi Gornick

- Proposal:

  - that we streamline video-making to continue expert feedback

  - this would need to reduce technical problems of editing

  - we would publish via Google/YouTube onto website

  - that website needs to be more accessible – How?

List of experts

- A shortlist of key experts needs to be made (reduced budget, high quality videos)

Final Event/s

- We need at least one blockbuster event with which to sign-off

- RSA April 09 is the leading contender – JW to check this out soon

- Any other contenders?

JW-